## User SOW
S# | MODULE | SUB MODULE | TASK DESCRIPTION | CHANGES TO BE INCORPORATED
1 | Onboarding | Login | 1. Create Login page • Integrate with mobiquity to fetch system token and Login validation • Basis mobiquity Login API response, route request to already existing Bulk dashboard in system. 2. User can also login via GP AD ID | 1. When any mobiquity user want access on Bulk Pay dashboard, then they have to get registered in BulkPay UI also with same login ID. So login ID of user in mobiquity and BulkUI DB should match.
2 | BillPayment Flow | Integration Changes | 1. On UI (named as CBP / web-portal-application) : to fetch bill details of accounts and to pay pending bills in bulk, request is initiated from UI and it is stored in CBP DB for further processing. At this point request is just queued, no fetching or processing has take place. 2. Second component scheduler will then pick these request from DB on timely basis and communicates with communicator component which will make hit to backend financial system(mobiquity) to fetch bill details or Payment request instead of Biller Platform. 3. In fetch bill details it is simple API hit to mobiquity to fetch bill details instead of biller platform. 4. For Payment also, communicator will send payment hit to just mobiquity. Not to biller. Mobiquity will in turn send hit to biller platform for any kind of third party integration. Communicator will not interact with biller platform. 5. While sending hit to mobiquity, CBP has to ensure a unique reference ID is created, stored in mflex DB corresponding to each bill request and is sent to mobiquity to manage for any disputes in future. | 1. Scheduler will pick only those records for enquiry for which they didn’t get response back from mobiquity platform. No retry feature will be available in this scenario. 2. If scheduler gets response back for payment API, then also any reference to the payments and third party response should be from mobiquity reports. It should not be checked from Bulk Billpay UI.
3 | Password Management Flow | New Flow | 1. Password management to be incorporated on Bulk UI portal in 2 ways: 2. Give forgot password option on login page. 3. User himself once logged in, can be given with Change password option | 1. All 2 APIs need to have direct integration with Mobiquity for forgot password and change password. 2. Mobiquity will share APIs to achieve same.

## EFFORTS (hidden)
Complete Web Application (Comviva - Grameen Phone)
S# | Module | Estimation (Hrs) | Assumptions
1 | Web - Frontend | 50 | 1. Development will be initiated post the code analysis and if there are any exceptions in the code will be resolved by the COMVIVA team
2 | Web - Backend | 125 | 2. Some of the integration like GP- AD login needs COMVIVA support
3 | Code Review & Analysis | 60 | 3. We wont be working on the Mobiquity API - Those will be provided by the COMVIVA, the only calling API via Mobiquity will alone be handled by our team
3 | PM + QA | 100 | 4. Need to share the exisiting APIs in the Postman collections are expected
4 | DevOps | 40 | 5. Database credentials / exisiting format need to be shared with the team
Total Efforts |  | 375 | 6. Password flow API needs to be shared with us by the COMVIVA team

## Timeline (hidden)
Modules | W1 | W2 | W3 | W4 | W5
Documentation & UI/UX
User - Frontend Development
User - Backend Development
QA
Devops
UAT & GO-LIVE